## Order flow
Comapany | category | Sales order no | Order Qty | order date | Pipe vendor | Pipe order date | Pipe receive date | vendor days | Nut available | Assembly | Packing | Dispatched | dispatch date | Order days | Note | Prority
IDOL | Job work | SO 554 | 20200 | 2026-05-17 | GP flex | 2026-05-23 | 2026-06-19 | 27 | TRUE | TRUE | TRUE | TRUE | 2026-07-21 | 65 | waiting for cover die, porduction started ?
Alpha sanitary | Nut set | SO 543 | 3000 | 2026-06-04 | In stock |  |  |  | TRUE | FALSE | TRUE | TRUE | 2026-06-09 | 125
Taiba traders | Job work | SO 541 | 350 | 2026-06-05 | In stock |  |  |  | TRUE | TRUE | TRUE | TRUE | 2026-06-09 | 124
Futura | Job work | SO 558 | 25000 | 2026-06-03 | Techno tube | 2026-06-18 | 2026-06-25 | 7 | TRUE | TRUE | TRUE | TRUE | 2026-06-30 | 27 | Pipe did not recived yet
Surya trading | Nut set | SO 549 | 3000 | 2026-06-11 | Techno tube |  |  |  | TRUE | FALSE | TRUE | TRUE | 2026-06-17 | 118
Gupta corp | Nut set | SO 548 | 20000 | 2026-06-12 | In stock |  |  |  | TRUE | FALSE | TRUE | TRUE | 2026-06-17 | 117
Surya trading | Job work | SO 559 | 4100 | 2026-06-11 | Techno tube | 2026-06-14 | 2026-06-25 | 11 | TRUE | TRUE | TRUE | TRUE | 2026-06-30 | 19 | pipe did not recived yet
Power skills | Nut set | SO 551 | 10000 | 2026-06-19 | 5M | 2026-06-19 | 2026-06-19 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-06-26 | 7 | need recive the next lot of nut set
Aura industries | Job work |  | 22500 | 2026-06-21 | GP flex | 2026-06-17 | 2026-07-04 | 17 | TRUE | TRUE | TRUE | TRUE | 2026-07-25 | 34 | pipe did not recived yet
Aura industries | Job work |  | 10000 | 2026-06-21 | Techno tube | 2026-06-22 | 2026-07-03 | 11 | TRUE | TRUE | TRUE | TRUE | 2026-07-07 | 16 | Production completed
GATIMAAN ENTERPRISES | Nut set | SO 557 | 10000 | 2026-06-22 | 5M | 2026-06-22 | 2026-06-22 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-07-14 | 22 | Waiting for payment from customer
Pawan Traders | Enflow CP | SO 559 | 1250 | 2026-06-22 | In stock | 2026-06-22 | 2026-06-22 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-07-06 | 14 | Production completed
Sk traders | Enflow CP | SO 560 | 3000 | 2026-06-23 | In stock | 2026-06-23 | 2026-06-23 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-06-30 | 7 | procssing
Hari enterprises | Enflow CP | SO 561 | 1300 | 2026-06-19 | In stock | 2026-06-19 | 2026-06-19 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-07-01 | 12
Sri Ashapura Industries | Nut set | SO 564 | 30000 | 2026-06-25 | 5M | 2026-06-25 | 2026-06-25 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-06-30 | 5
KANGANA AGENCY | Nut set |  | 10000 | 2026-06-25 | In stock | 2026-06-25 | 2026-06-25 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-06-26 | 1
Ceraflo | Job work | SO 566 | 2000 | 2026-07-01 | Enflow 2 | 2026-07-01 | 2026-07-06 | 5 | TRUE | TRUE | TRUE | TRUE | 2026-07-11 | 10
CR polymers | Nut set | SO 567 | 10000 | 2026-07-01 | 5M | 2026-07-01 | 2026-07-01 | 0 | TRUE | FALSE | TRUE | TRUE |  | 98
Vojal | Job work | SO 568 | 2000 | 2026-07-01 | Enflow 2 | 2026-07-01 | 2026-07-06 | 5 | TRUE | TRUE | TRUE | TRUE | 2026-07-11 | 10
Futura | Job work |  | 150 | 2026-07-01 | Enflow 2 | 2026-07-01 | 2026-07-06 | 5 | TRUE | TRUE | TRUE | TRUE | 2026-07-08 | 7
New poonam hardware | Enflow CP | SO 569 | 600 | 2026-07-03 | In stock | 2026-07-03 | 2026-07-03 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-07-06 | 3
LOKENATH MEDICAL HALL | Nut set | SO 565 | 1000 | 2026-06-27 | In stock | 2026-07-27 | 2026-07-27 | 0 | TRUE | FALSE | TRUE | TRUE |  | 102
New poonam hardware | Job work | SO 569 | 600 | 2026-07-06 | In stock | 2026-07-06 | 2026-07-06 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-07-07 | 1
CS WATERTAP | Job work | SO 571 | 20000 | 2026-07-07 | Techno tube | 2026-07-09 | 2026-07-17 | 8 | TRUE | TRUE | TRUE | TRUE | 2026-07-27 | 20 | order pipe to techno tube
Futura | Job work | SO 575 | 300 | 2026-07-08 | Enflow 2 | 2026-07-08 | 2026-07-11 | 3 | TRUE | TRUE | TRUE | TRUE | 2026-07-13 | 5
New poonam hardware | Enflow CP |  | 600 | 2026-07-11 | In stock | 2026-07-11 | 2026-07-11 | 0 | FALSE | FALSE | FALSE | TRUE |  | 88 | order not conformed
shanti marketing | Nut set | SO 576 | 3000 | 2026-07-15 | In stock | 2026-07-15 | 2026-07-15 | 0 | TRUE | FALSE | TRUE | TRUE |  | 84
LOKENATH MEDICAL HALL | Nut set | SO 577 | 1000 | 2026-07-17 | In stock | 2026-07-17 | 2026-07-17 | 0 | TRUE | FALSE | TRUE | TRUE |  | 82
Aura industries | Job work | SO 593 | 26500 | 2026-07-20 | Enflow 2 | 2026-07-28 | 2026-08-08 | 11 | TRUE | TRUE | TRUE | TRUE | 2026-08-10 | 21
Aura industries | Job work | SO 594 | 12000 | 2026-07-20 | Enflow 2 | 2026-07-28 | 2026-08-08 | 11 | TRUE | TRUE | TRUE | TRUE | 2026-08-10 | 21
Gupta corp | Nut set | SO 578 | 20000 | 2026-07-21 | In stock | 2026-07-21 | 2026-07-21 | 0 | TRUE | FALSE | TRUE | TRUE |  | 78
Premier Marketing | Nut set | SO 579 | 5000 | 2026-07-21 | In stock | 2026-07-21 | 2026-07-21 | 0 | TRUE | FALSE | TRUE | TRUE |  | 78
Sri Ashapura Industries | Nut set | SO 580 | 50000 | 2026-07-23 | In stock | 2026-07-23 | 2026-07-23 | 0 | TRUE | FALSE | TRUE | TRUE |  | 76
NAVEEN PRODUCTS | Nut set | So 583 | 5000 | 2026-07-27 | In stock | 2026-07-27 | 2026-07-27 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-07-28 | 1
Vojal | Job work | SO 597 | 2200 | 2026-07-27 | Enflow 2 | 2026-07-29 | 2026-08-12 | 14 | TRUE | TRUE | TRUE | TRUE | 2026-08-13 | 17
JJ marketing | Nut set | SO 588 | 10000 | 2026-07-31 | In stock | 2026-07-31 | 2026-07-31 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-08-05 | 5
Schintler | Job work | SO 589 | 12500 | 2026-07-31 | Enflow 2 | 2026-07-31 | 2026-08-12 | 12 | TRUE | TRUE | TRUE | TRUE | 2026-08-20 | 20
Alpha sanitary | Nut set | SO 590 | 3000 | 2026-08-03 | In stock | 2026-08-03 | 2026-08-03 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-08-05 | 2
EZIYFLO POLYPLAST | Nut set | SO 591 | 20000 | 2026-08-03 | In stock | 2026-08-03 | 2026-08-03 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-08-05 | 2
MAHALAKSHMI ENTERPRISES | Enflow CP | SO 592 | 1600 | 2026-08-06 | In stock | 2026-08-06 | 2026-08-06 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-08-21 | 15
IDOL | Job work | SO 595 | 10000 | 2026-08-08 | Enflow 2 | 2026-08-10 | 2026-08-19 | 9 | TRUE | TRUE | TRUE | TRUE | 2026-09-02 | 25
Schintler | Job work | SO 599 | 7500 | 2026-08-14 | Enflow 2 | 2026-08-17 |  | 51 | TRUE | TRUE | TRUE | TRUE | 2026-09-09 | 26
Aura industries | Job work | SO 600 | 29500 | 2026-08-16 | Enflow 2 | 2026-08-17 | 2026-09-15 | 29 | TRUE | TRUE | TRUE | TRUE | 2026-09-16 | 31
Aura industries | Job work | SO 601 | 15000 | 2026-08-16 | Enflow 2 | 2026-08-17 | 2026-09-15 | 29 | TRUE | TRUE | TRUE | TRUE | 2026-09-16 | 31
Blue Star | Nut set | SO 602 | 26000 | 2026-08-14 | 5M | 2026-08-17 | 2026-08-17 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-08-21 | 7
Mathaji electrical haedware | Enflow CP | SO 598 | 1500 | 2026-08-17 | In stock | 2026-08-17 | 2026-08-17 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-08-25 | 8
CS WATERTAP | Job work | 611 | 3000 | 2026-08-17 | Enflow 2 | 2026-08-27 | 2026-09-05 | 9 | TRUE | TRUE | TRUE | TRUE | 2026-09-05 | 19
EZIYFLO POLYPLAST | Pipe | SO 596 | 112 rolls | 2026-08-17 | Enflow 2 | 2026-08-17 |  | 51 | TRUE | FALSE | TRUE | TRUE | 2026-08-22 | 5
S K traders | Enflow CP | SO 606 | 1130 | 2026-08-18 | In stock | 2026-08-18 | 2026-08-18 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-08-28 | 10
GATIMAAN ENTERPRISES | Nut set | SO 603 | 10000 | 2026-08-22 | 5M | 2026-08-22 | 2026-08-22 | 0 | FALSE | FALSE | FALSE | TRUE |  | 46 | customer not responding
BHARUCHI INDUSTRIES | Nut set | SO 604 | 5000 | 2026-08-24 | 5M | 2026-08-24 | 2026-08-24 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-08-27 | 3
Sri Ashapura Industries | Nut set | SO 605 | 50000 | 2026-08-24 | 5M | 2026-08-24 | 2026-08-24 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-08-27 | 3
Vojal | Job work | SO 607 | 2300 | 2026-08-20 | Enflow 2 | 2026-08-20 |  | 48 | TRUE | TRUE | TRUE | TRUE | 2026-09-08 | 19
S K traders | Enflow CP | SO 608 | 4100 | 2026-08-28 | Enflow 2 | 2026-08-28 | 2026-08-28 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-07 | 10
Alpha sanitary | Nut set | 613 | 1000 | 2026-08-31 | 5M | 2026-08-31 | 2026-08-31 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-08 | 8
Hari enterprises | Enflow CP | 610 | 1000 | 2026-08-31 | In stock | 2026-08-31 | 2026-08-31 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-07 | 7
Ashva poly plast | Job work | 612 | 4500 | 2026-09-04 | Enflow 2 | 2026-09-05 | 2026-09-15 | 10 | TRUE | TRUE | TRUE | FALSE |  | 33
EZIYFLO POLYPLAST | Nut set | 615 | 20000 | 2026-09-05 | In stock | 2026-09-05 | 2026-09-05 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-08 | 3
Blue Star | Pipe | 609 | 1000 | 2026-09-02 | Enflow 2 | 2026-09-02 | 2026-09-07 | 5 | TRUE | FALSE | TRUE | TRUE | 2026-09-08 | 6
SHRI SAI SAMARTH ENTERPRISES | Pipe | 614 | 2350 | 2026-08-20 | Enflow 2 | 2026-08-20 | 2026-09-07 | 18 | TRUE | FALSE | TRUE | TRUE | 2026-09-08 | 19
Alpha sanitary | Pipe | 613 | 1500 | 2026-08-31 | Enflow 2 | 2026-08-31 | 2026-09-07 | 7 | TRUE | FALSE | TRUE | TRUE | 2026-09-08 | 8
CS WATERTAP | Job work | 617 | 20000 | 2026-09-07 | Enflow 2 | 2026-09-07 | 2026-09-26 | 19 | TRUE | TRUE | TRUE | TRUE | 2026-09-28 | 21
Zera coat | Nut set | 609 | 2000 | 2026-09-10 | In stock | 2026-09-10 | 2026-09-10 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-16 | 6
Vojal | Job work | 618 | 2100 | 2026-09-10 | Enflow 2 | 2026-09-11 | 2026-09-15 | 4 | TRUE | TRUE | TRUE | TRUE | 2026-09-23 | 13
Laxmi Metaplast Industries | Nut set | 616 | 6000 | 2026-09-12 | In stock | 2026-09-12 | 2026-09-12 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-16 | 4
Alpha sanitary | Pipe | 628 | 2600 | 2026-09-15 | Enflow 2 | 2026-09-15 | 2026-09-26 | 11 | FALSE | FALSE | TRUE | TRUE | 2026-09-28 | 13
Shri Ambika Plast | Enflow CP | 619 | 310 | 2026-09-15 | In stock | 2026-09-15 | 2026-09-15 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-21 | 6
Pipeart | Nut set | 620 | 5000 | 2026-09-16 | In stock | 2026-09-16 | 2026-09-16 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-19 | 3
Taiba traders | Enflow CP | 621 | 500 | 2026-09-16 | In stock | 2026-09-16 | 2026-09-16 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-23 | 7
Gupta corp | Nut set |  | 20000 | 2026-09-16 | In stock | 2026-09-16 | 2026-09-16 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-19 | 3
Futura | Job work |  | 3500 | 2026-09-17 | Enflow 2 | 2026-09-17 |  | 20 | TRUE | FALSE | FALSE | TRUE | 2026-09-22 | 5 | 500 pcs of 24 inch pending
Riyyo industries | Nut set | 623 | 1000 | 2026-09-19 | In stock | 2026-09-19 | 2026-09-19 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-23 | 4
Ceraflo | Job work | 625 | 2000 | 2026-09-21 | Enflow 2 | 2026-09-21 | 2026-09-26 | 5 | TRUE | TRUE | TRUE | TRUE | 2026-09-28 | 7
new poonam hardware | Enflow CP |  | 600 | 2026-09-21 | In stock | 2026-09-21 | 2026-09-21 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-10-03 | 12
BHOOMI ENTERPRISES | Job work | EST-123 | 6500 | 2026-09-24 | Enflow 2 | 2026-09-24 |  | 13 | TRUE | TRUE | TRUE | TRUE | 2026-10-07 | 13
Aura industries | Job work |  | 34900 | 2026-09-24 | Enflow 2 | 2026-09-25 |  | 12 | TRUE | FALSE | FALSE | FALSE |  | 13
Aura industries | Job work |  | 22500 | 2026-09-24 | Enflow 2 | 2026-09-18 |  | 19 | TRUE | FALSE | FALSE | FALSE |  | 13
Alpha sanitary | Nut set | 628 | 2000 | 2026-09-28 | In stock | 2026-09-28 | 2026-09-28 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-28 | 0
Ashapura industries | Nut set | 629 | 50000 | 2026-09-28 | In stock | 2026-09-28 | 2026-09-28 | 0 | TRUE | TRUE | TRUE | TRUE | 2026-09-29 | 1
NIRMAL SALES AND SERVICES | Pipe | 630 | 2 rolls | 2026-09-30 | Enflow 2 | 2026-09-30 | 2026-09-30 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-30 | 0
NIRMAL SALES AND SERVICES | Nut set | 630 | 1000 | 2026-09-30 | In stock | 2026-09-30 | 2026-09-30 | 0 | TRUE | FALSE | TRUE | TRUE | 2026-09-30 | 0
EZIYFLO POLYPLAST INDUSTRIES | Nut set | SO-634 | 20000 | 2026-10-05 | In stock | 2026-10-05 |  | 2 | TRUE | TRUE | TRUE | TRUE | 2026-10-06 | 1
Formulas:
vendor days = IF([Pipe order date]="","",IF([Pipe receive date]="",TODAY()-[Pipe order date],[Pipe receive date]-[Pipe order date]))
Order days = IF([order date]="","",IF([dispatch date]="",TODAY()-[order date],[dispatch date]-[order date]))

## WIP_SHEET
WO NO | ORDER DATE | DISPATCH DATE | COMPANY NAME | WORK CATEGORY | BRAND | TYPE | SIZE | DISCRIPTION | QTY | PIPE VENDOR | PIPE ORDER | NUT SET ORDER | PIPE CUT | PIPE ASSEMBLY | COVER PACKAGING | LABEL APPLY | MATERIAL SENT | YET TO DISPATCH | done
1 | 2026-05-31 | 2026-06-20 | AURA | JW | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[5 empty] | MARINO ST | Non-Braided | 1 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[5 empty] | PLAIN ST | Non-Braided | 1 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | - | - | 2000 | 0 | done
[5 empty] | WF CP | Non-Braided | 24 | CONNECTION PIPE WL | 6000 | GP | C | C | C | C | - | - | 6000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 1992 | GP | C | C | C | C | - | - | 1992 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 1000 | GP | C | C | C | C | - | - | 1000 | 0 | done
[5 empty] | MARINO CP | Non-Braided | 24 | CONNECTION PIPE WL | 4540 | GP | C | C | C | C | - | - | 4540 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 1450 | GP | C | C | C | C | - | - | 1450 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 750 | GP | C | C | C | C | - | - | 750 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL | 500 | GP | C | C | C | C | - | - | 500 | 0 | done
2 | 2026-06-03 | 2026-06-24 | FUTURA | JW | FUTURA ST | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 25000 | TT | C | C | - | C | C | C | 25000 | 0 | done
3 | 2026-06-04 | 2026-06-11 | ALPHA SANITARY | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 3000 | 5M | - | - | - | - | - | - | 3000 | 0 | done
4 | 2026-06-05 | 2026-06-12 | BADSHAH BELGAUM | JW | ENFLOW CP | Non-Braided | 12 | CONNECTION PIPE WL L-RTK | 50 | TT | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WL L-RTK | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-RTK | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 50 | TT | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL L-RTK | 50 | TT | C | C | C | C | C | C | 50 | 0 | done
5 | 2026-06-11 | 2026-06-25 | SURYA TRADING | JW | PLAIN ST | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 300 | TT | C | C | C | C | C | C | 300 | 0 | done
6 | 2026-06-11 | 2026-06-25 | SURYA TRADING | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 3000 | 5M | - | - | - | - | - | - | 3000 | 0 | done
7 | 2026-06-11 | 2026-06-25 | SURYA TRADING | JW | SURYA ULTRA ST | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 2000 | TT | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 300 | TT | C | C | C | C | C | C | 300 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WN L-RTK | 300 | TT | C | C | C | C | C | C | 300 | 0 | done
8 | 2026-06-12 | 2026-06-26 | GUPTA CROP | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 20000 | 5M | - | - | - | - | - | - | 20000 | 0 | done
[5 empty] | Nut Loose Spare | Nut Loose Spare |  | L-INNER | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
[6 empty] | Nut Loose Spare |  | L-CAP | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
[6 empty] | Nut Loose Spare |  | WASHER | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
9 | 2026-06-17 | 2026-07-15 | IDOL | JW | IDOL CP | Braided | 18 | CONNECTION PIPE WL L-HTK | 3800 | GP | C | C | C | C | C | C | 3800 | 0 | done
[6 empty] | Braided | 24 | CONNECTION PIPE WL L-HTK | 12000 | GP | C | C | C | C | C | C | 12000 | 0 | done
[6 empty] | Braided | 30 | CONNECTION PIPE WL L-HTK | 200 | GP | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Braided | 36 | CONNECTION PIPE WL L-HTK | 200 | GP | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Braided | 1 M | CONNECTION PIPE WL L-HTK | 3800 | GP | C | C | C | C | C | C | 3800 | 0 | done
[6 empty] | Braided | 1.5 M | CONNECTION PIPE WL L-HTK | 200 | GP | C | C | C | C | C | C | 200 | 0 | done
10 | 2026-06-19 | 2026-06-23 | POWER SKILLS | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
11 | 2026-06-22 | 2026-07-10 | AURA | JW | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 3500 | TT | C | C | C | C | C | C | 3500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 2000 | TT | C | C | C | C | C | C | 2000 | 0 | done
[5 empty] | MARINO ST | Non-Braided | 1 M | CONNECTION PIPE WN | 3000 | TT | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 1500 | TT | C | C | C | C | C | C | 1500 | 0 | done
[5 empty] | WF CP | Non-Braided | 24 | CONNECTION PIPE WL | 6000 | GP | C | C | C | C | C | C | 6000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 1500 | GP | C | C | C | C | C | C | 1500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 1000 | GP | C | C | C | C | C | C | 1000 | 0 | done
[5 empty] | MARINO CP | Non-Braided | 18 | CONNECTION PIPE WL | 2000 | GP | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL | 8000 | GP | C | C | C | C | C | C | 8000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 3000 | GP | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 1000 | GP | C | C | C | C | C | C | 1000 | 0 | done
12 | 2026-06-22 | 2026-06-30 | Shri krishna Enterprises | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
13 | 2026-06-22 | 2026-06-30 | Pawan Traders | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL L-RTK | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL L-RTK | 50 | TT | C | C | C | C | C | C | 50 | 0 | done
14 | 2026-06-23 | 2026-07-08 | SK Traders | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 2000 | TT | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
15 | 2026-06-25 | 2026-06-30 | Hari Enterprise | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WL | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 200 | TT | C | C | C | C | C | C | 200 | 0 | done
16 | 2026-06-25 | 2026-06-29 | KANGANA AGENCY | NS | Nut Loose Spare | Nut Loose Spare | - | LIGHT KEY | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
17 | 2026-06-25 | 2026-06-29 | Sri Ashapura Industries | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 30000 | 5M | - | - | - | - | - | - | 30000 | 0 | done
18 | 2026-06-30 | 2026-07-03 | LOKENATH MEDICAL HALL | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 1000 | 5M | - | - | - | - | - | - | 1000 | 0 | done
19 | 2026-06-30 | 2026-07-03 | LOKENATH MEDICAL HALL | NS | Nut Loose Spare | Nut Loose Spare | - | K-Washer | 1000 | 5M | - | - | - | - | - | - | 1000 | 0 | done
20 | 2026-07-01 | 2026-07-07 | CR POLYMERSS | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
21 | 2026-07-01 | 2026-07-21 | CERAFLO | JW | CERAFLO CP | Non-Braided | 12 | CONNECTION PIPE WC L-RTK | 100 | TT | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WC L-RTK | 500 | TT | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WC L-RTK | 500 | TT | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WC L-RTK | 500 | TT | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WC L-RTK | 400 | TT | C | C | C | C | C | C | 400 | 0 | done
22 | 2026-07-01 | 2026-07-21 | VOJAL | JW | VOJAL | Non-Braided | 18 | CONNECTION PIPE WN L-HTK | 400 | TT | C | C | C | C | C | C | 400 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 400 | TT | C | C | C | C | C | C | 400 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 600 | TT | C | C | C | C | C | C | 600 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 600 | TT | C | C | C | C | C | C | 600 | 0 | done
23 | 2026-07-01 | 2026-07-21 | FUTURA | JW | FUTURA ST | Non-Braided | 40 | CONNECTION PIPE WN L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 80 | CONNECTION PIPE WN L-HTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
24 | 2026-07-03 | 2026-07-24 | NEW POONAM HARDWARE | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
25 | 2026-07-07 | 2026-07-28 | CS WATER TAP | JW | CS WATER TAP ST | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 10000 | TT | C | C | C | C | C | C | 10000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 6000 | TT | C | C | C | C | C | C | 6000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 2000 | TT | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WN L-RTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
26 | 2026-07-08 | 2026-07-22 | FUTURA | JW | FUTURA ST | Non-Braided | 30 | CONNECTION PIPE WN L-HTK | 300 | ENFLOW2 | C | C | C | C | C | C | 300 | 0 | done
27 | 2026-07-14 | 2026-07-28 | NEW POONAM HARDWARE | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
28 | 2026-07-15 | 2026-07-30 | SHANTI MARKETING | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 2000 | 5M | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Nut spare | - | ROUND TYPE NUT SET | 1000 | 5M | C | C | C | C | C | C | 1000 | 0 | done
29 | 2026-07-17 | 2026-07-28 | LOKENATH MEDICAL HALL | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 1000 | 5M | C | C | C | C | C | C | 1000 | 0 | done
30 | 2026-07-20 | 2026-08-03 | AURA | JW | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 2000 | ENFLOW2 | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 2000 | ENFLOW2 | C | C | C | C | C | C | 2000 | 0 | done
[5 empty] | MARINO ST | Non-Braided | 1 M | CONNECTION PIPE WN | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[5 empty] | PLAIN ST | Non-Braided | 1 M | CONNECTION PIPE WN | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[5 empty] | WF CP | Non-Braided | 18 | CONNECTION PIPE WL | 2500 | ENFLOW2 | C | C | C | C | C | C | 2500 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL | 8000 | ENFLOW2 | C | C | C | C | C | C | 8000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 2500 | ENFLOW2 | C | C | C | C | C | C | 2500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[5 empty] | MARINO CP | Non-Braided | 18 | CONNECTION PIPE WL | 2000 | ENFLOW2 | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL | 8000 | ENFLOW2 | C | C | C | C | C | C | 8000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL | 1500 | ENFLOW2 | C | C | C | C | C | C | 1500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
31 | 2026-07-22 | 2026-07-31 | PREMIER MARKETING | NS | NUT SET | Nut spare | - | Round TYPE NUT SET | 5000 | 5M | - | - | - | - | - | - | 5000 | 0 | done
32 | 2026-07-23 | 2026-07-31 | Sri Ashapura Industries | NS | NUT SET | Nut spare | - | Round TYPE NUT SET | 50000 | 5M | - | - | - | - | - | - | 50000 | 0 | done
33 | 2026-07-27 | 2026-07-29 | NAVEEN PRODUCTS | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 5000 | 5M | - | - | - | - | - | - | 5000 | 0 | done
34 | 2026-07-27 | 2026-07-29 | NAVEEN PRODUCTS | NS | Nut Loose Spare | Nut Loose Spare | - | M-Inner | 30000 | 5M | - | - | - | - | - | - | 30000 | 0 | done
35 | 2026-07-27 | 2026-07-29 | NAVEEN PRODUCTS | NS | Nut Loose Spare | Nut Loose Spare | - | M-Cap | 30000 | 5M | - | - | - | - | - | - | 30000 | 0 | done
36 | 2026-07-27 | 2026-07-29 | NAVEEN PRODUCTS | NS | Nut Loose Spare | Nut Loose Spare | - | WASHER | 40000 | 5M | - | - | - | - | - | - | 40000 | 0 | done
37 | 2026-07-28 | 2026-08-11 | VOJAL | JW | VOJAL | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
38 | 2026-07-28 | 2026-08-11 | VOJAL | JW | ARTIMIST | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 300 | ENFLOW2 | C | C | C | C | C | C | 300 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 700 | ENFLOW2 | C | C | C | C | C | C | 700 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 300 | ENFLOW2 | C | C | C | C | C | C | 300 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
39 | 2026-07-31 | 2026-08-11 | JJ Marketing | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 8000 | 5M | - | - | - | - | - | - | 8000 | 0 | done
[6 empty] | Nut spare | - | Round TYPE NUT SET | 2000 | 5M | - | - | - | - | - | - | 2000 | 0 | done
40 | 2026-07-31 | 2026-08-18 | SCHINTLER | JW | SCHINTLER CP | Non-Braided | 18 | CONNECTION PIPE WL L-HTK | 10000 | ENFLOW2 | C | C | C | C | C | C | 10000 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 2500 | ENFLOW2 | C | C | C | C | C | C | 2500 | 0 | done
41 | 2026-08-03 | 2026-08-09 | ALPHA SANITARY | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 3000 | 5M | - | - | - | - | - | - | 3000 | 0 | done
42 | 2026-08-03 | 2026-08-09 | EZIYFLO POLYPLAST | NS | Nut Loose Spare | Nut Loose Spare | - | WASHER | 20000 | 5M | - | - | - | - | - | - | 20000 | 0 | done
43 | 2026-08-10 | 2026-08-24 | IDOL | JW | IDOL CP | Braided | 30 | CONNECTION PIPE WL L-HTK | 5000 | ENFLOW2 | C | C | C | C | C | C | 5000 | 0 | done
[6 empty] | Braided | 36 | CONNECTION PIPE WL L-HTK | 5000 | ENFLOW2 | C | C | C | C | C | C | 5000 | 0 | done
44 | 2026-08-10 | 2026-08-24 | MAHALAKSHMI ENTERPRISES | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 300 | ENFLOW2 | C | C | C | C | C | C | 300 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 300 | ENFLOW2 | C | C | C | C | C | C | 300 | 0 | done
45 | 2026-08-17 | 2026-08-31 | AURA | JW | WF CP | Braided | 18 | CONNECTION PIPE WL | 2500 | ENFLOW2 | C | C | C | C | C | C | 2500 | 0 | done
[6 empty] | Braided | 24 | CONNECTION PIPE WL | 8000 | ENFLOW2 | C | C | C | C | C | C | 8000 | 0 | done
[6 empty] | Braided | 1 M | CONNECTION PIPE WL | 4000 | ENFLOW2 | C | C | C | C | C | C | 4000 | 0 | done
[6 empty] | Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Braided | 2 M | CONNECTION PIPE WL | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[5 empty] | MARINO CP | Braided | 18 | CONNECTION PIPE WL | 2000 | ENFLOW2 | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Braided | 24 | CONNECTION PIPE WL | 7000 | ENFLOW2 | C | C | C | C | C | C | 7000 | 0 | done
[6 empty] | Braided | 1 M | CONNECTION PIPE WL | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Braided | 2 M | CONNECTION PIPE WL | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[5 empty] | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 4500 | ENFLOW2 | C | C | C | C | C | C | 4500 | 0 | done
[5 empty] | MARINO ST | Non-Braided | 1 M | CONNECTION PIPE WN | 4000 | ENFLOW2 | C | C | C | C | C | C | 4000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 4500 | ENFLOW2 | C | C | C | C | C | C | 4500 | 0 | done
[5 empty] | PLAIN ST | Non-Braided | 1.5 M | CONNECTION PIPE WN | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
46 | 2026-08-17 | 2026-08-31 | SCHINTLER | JW | SCHINTLER CP | Non-Braided | 18 | CONNECTION PIPE WL L-HTK | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 4500 | ENFLOW2 | C | C | C | C | C | C | 4500 | 0 | done
47 | 2026-08-17 | 2026-08-31 | BLUE STAR | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 20000 | 5M | - | - | - | - | - | - | 20000 | 0 | done
[6 empty] | Nut spare | - | Round TYPE NUT SET | 6000 | 5M | - | - | - | - | - | - | 6000 | 0 | done
48 | 2026-08-17 | 2026-08-31 | Mathaji electrical hardware and co | JW | ENFLOW CP | Non-Braided | 12 | CONNECTION PIPE WL L-HTK | 250 | ENFLOW2 | C | C | C | C | C | C | 250 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WL L-HTK | 250 | ENFLOW2 | C | C | C | C | C | C | 250 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-HTK | 250 | ENFLOW2 | C | C | C | C | C | C | 250 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 3 M | CONNECTION PIPE WL L-HTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
49 | 2026-08-17 | 2026-08-31 | CS WATER TAP | JW | CS WATER TAP ST | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 1500 | TT | C | C | C | C | C | C | 1500 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 10000 | TT | C | C | C | C | C | C | 10000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 7000 | TT | C | C | C | C | C | C | 7000 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 1000 | TT | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WN L-RTK | 500 | TT | C | C | C | C | C | C | 500 | 0 | done
50 | 2026-08-18 | 2026-08-31 | SK Traders | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
51 | 2026-08-17 | 2026-08-22 | EZIYFLO POLYPLAST | Pipe | OTTERTEC | Non-Braided | 18 | PIPE ROLL | 10 | ENFLOW2 | - | - | - | - | - | - | 10 | 0 | done
[6 empty] | Non-Braided | 24 | PIPE ROLL | 27 | ENFLOW2 | - | - | - | - | - | - | 27 | 0 | done
[6 empty] | Non-Braided | 1 M | PIPE ROLL | 50 | ENFLOW2 | - | - | - | - | - | - | 50 | 0 | done
[6 empty] | Non-Braided | 1.5 M | PIPE ROLL | 25 | ENFLOW2 | - | - | - | - | - | - | 25 | 0 | done
52 | 2026-08-20 | 2026-08-31 | VOJAL | JW | VOJAL | Non-Braided | 12 | CONNECTION PIPE WN L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 12 | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WN L-HTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 18 | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 150 | ENFLOW2 | C | C | C | C | C | C | 150 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
53 | 2026-08-20 | 2026-08-31 | VOJAL | JW | ARTIMIST | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 250 | ENFLOW2 | C | C | C | C | C | C | 250 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
54 | 2026-08-22 | 2026-08-31 | GATIMAAN ENTERPRISES | NS | NUT SET | Nut spare | - | Round TYPE NUT SET | - | 5M | Order Cancelled | [6 empty] | - | done
55 | 2026-08-24 | 2026-08-31 | BHARUCHI INDUSTRIES | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 5000 | 5M | - | - | - | - | - | - | 5000 | 0 | done
56 | 2026-08-25 | 2026-08-31 | Sri Ashapura Industries | NS | NUT SET | Nut spare | - | Round TYPE NUT SET | 50000 | 5M | - | - | - | - | - | - | 50000 | 0 | done
57 | 2026-08-27 | 2026-08-31 | SK Traders | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 2000 | ENFLOW2 | C | C | C | C | C | C | 2000 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 1000 | ENFLOW2 | C | C | C | C | C | C | 1000 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
58 | 2026-08-31 | 2026-09-07 | ALPHA SANITARY | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 1000 | 5M | - | - | - | - | - | - | 1000 | 0 | done
59 | 2026-08-31 | 2026-09-07 | Hari Enterprise | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WL L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL L-RTK | 150 | ENFLOW2 | C | C | C | C | C | C | 150 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
60 | 2026-09-05 | 2026-09-20 | ASHVA POLYPLAST | JW | AKANT | Non-Braided | 24 | CONNECTION PIPE WL L-RTK | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 40 | CONNECTION PIPE WL L-RTK | 1500 | ENFLOW2 | C | C | C | C | C | C | 1500 | 0 | done
61 | 2026-09-07 | 2026-09-08 | EZIYFLO POLYPLAST | NS | Nut Loose Spare | Nut Loose Spare | - | WASHER | 20000 | 5M | - | - | - | - | - | - | 20000 | 0 | done
62 | 2026-09-10 | 2026-09-18 | BLUE STAR | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 2000 | 5M | C | C | C | C | C | C | 2000 | 0 | done
63 | 2026-09-11 | 2026-09-30 | VOJAL | JW | VOJAL | Non-Braided | 18 | CONNECTION PIPE WN L-HTK | 400 | ENFLOW2 | C | C | C | C | C | C | 400 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WN L-RTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-HTK | 150 | ENFLOW2 | C | C | C | C | C | C | 150 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WN L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN L-RTK | 150 | ENFLOW2 | C | C | C | C | C | C | 150 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WN L-HTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WN L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
64 | 2026-09-12 | 2026-09-19 | LAXMI METAPLAST INDUSTRIES | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 6000 | 5M | - | - | - | - | - | - | 6000 | 0 | done
65 | 2026-09-16 | 2026-09-21 | Shri Ambika Plast | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WC L-RTK | 30 | ENFLOW2 | C | C | C | C | C | C | 30 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WC L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WC L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WC L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WC L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 3 M | CONNECTION PIPE WC L-RTK | 30 | ENFLOW2 | C | C | C | C | C | C | 30 | 0 | done
66 | 2026-09-16 | 2026-09-30 | PIPEART | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 5000 | 5M | - | - | - | - | - | - | 5000 | 0 | done
67 | 2026-09-16 | 2026-09-30 | TAIBA TRADERS | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WC L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WC L-RTK | 200 | ENFLOW2 | C | C | C | C | C | C | 200 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WC L-RTK | 100 | ENFLOW2 | C | C | C | C | C | C | 100 | 0 | done
68 | 2026-09-17 | 2026-09-30 | GUPTA CROP | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
[6 empty] | Nut spare | - | Round TYPE NUT SET | 10000 | 5M | - | - | - | - | - | - | 10000 | 0 | done
69 | 2026-09-17 | 2026-09-30 | FUTURA | JW | FUTURA ST | Non-Braided | 18 | CONNECTION PIPE WN L-HTK | 3000 | ENFLOW2 | C | C | C | C | C | C | 3000 | 0 | done
[6 empty] | Non-Braided | 36 | CONNECTION PIPE WN L-HTK | 5000 | ENFLOW2 | C | C | C | C | C | C | 5000 | 0 | done
70 | 2026-09-21 | 2026-09-30 | CERAFLO | JW | CERAFLO CP | Non-Braided | 18 | CONNECTION PIPE WC L-RTK | 200 | ENFLOW2 | [7 empty] | 200
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WC L-RTK | 1500 | ENFLOW2 | [7 empty] | 1500
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WC L-RTK | 300 | ENFLOW2 | [7 empty] | 300
71 | 2026-09-21 | 2026-09-30 | NEW POONAM HARDWARE | JW | ENFLOW CP | Non-Braided | 24 | CONNECTION PIPE WC L-HTK | 500 | ENFLOW2 | C | C | C | C | C | C | 500 | 0 | done
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WC L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WC L-RTK | 50 | ENFLOW2 | C | C | C | C | C | C | 50 | 0 | done
72 | 2026-09-23 | 2026-09-29 | RIYYO INDUSTRIES | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 1000 | 5M | - | - | - | - | - | - | 1000 | 0 | done
73 | 2026-09-24 | 2026-09-30 | BHOOMI ENTERPRISES | JW | ENFLOW CP | Non-Braided | 18 | CONNECTION PIPE WL L-RTK | 500 | ENFLOW2 | [7 empty] | 500
[6 empty] | Non-Braided | 24 | CONNECTION PIPE WL L-RTK | 3000 | ENFLOW2 | [7 empty] | 3000
[6 empty] | Non-Braided | 1 M | CONNECTION PIPE WL L-RTK | 2000 | ENFLOW2 | [7 empty] | 2000
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WL L-RTK | 500 | ENFLOW2 | [7 empty] | 500
[6 empty] | Non-Braided | 2 M | CONNECTION PIPE WL L-RTK | 500 | ENFLOW2 | [7 empty] | 500
74 | 2026-09-25 | 2026-10-20 | AURA | JW | WF CP | Braided | 18 | CONNECTION PIPE WL | 4000 | ENFLOW2 | [7 empty] | 4000
[6 empty] | Braided | 24 | CONNECTION PIPE WL | 10000 | ENFLOW2 | [7 empty] | 10000
[6 empty] | Braided | 1 M | CONNECTION PIPE WL | 4000 | ENFLOW2 | [7 empty] | 4000
[6 empty] | Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | [7 empty] | 1000
[6 empty] | Braided | 2 M | CONNECTION PIPE WL | 400 | ENFLOW2 | [7 empty] | 400
[5 empty] | MARINO CP | Braided | 18 | CONNECTION PIPE WL | 2500 | ENFLOW2 | [7 empty] | 2500
[6 empty] | Braided | 24 | CONNECTION PIPE WL | 10000 | ENFLOW2 | [7 empty] | 10000
[6 empty] | Braided | 1 M | CONNECTION PIPE WL | 2000 | ENFLOW2 | [7 empty] | 2000
[6 empty] | Braided | 1.5 M | CONNECTION PIPE WL | 1000 | ENFLOW2 | [7 empty] | 1000
[5 empty] | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 1000 | ENFLOW2 | [7 empty] | 1000
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 6000 | ENFLOW2 | [7 empty] | 6000
[5 empty] | MARINO ST | Non-Braided | 1 M | CONNECTION PIPE WN | 5000 | ENFLOW2 | [7 empty] | 5000
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 6000 | ENFLOW2 | [7 empty] | 6000
[5 empty] | PLAIN ST | Non-Braided | 1 M | CONNECTION PIPE WN | 2000 | ENFLOW2 | [7 empty] | 2000
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 1500 | ENFLOW2 | [7 empty] | 1500
[5 empty] | WF ST | Non-Braided | 1 M | CONNECTION PIPE WN | 500 | ENFLOW2 | [7 empty] | 500
[6 empty] | Non-Braided | 1.5 M | CONNECTION PIPE WN | 500 | ENFLOW2 | [7 empty] | 500
75 | 2026-09-28 | 2026-09-30 | Sri Ashapura Industries | NS | NUT SET | Nut spare | - | ROUND TYPE NUT SET | 50000 | 5M | - | - | - | - | - | - | 50000 | 0 | done
76 | 2026-09-28 | 2026-09-30 | ALPHA SANITARY | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 2000 | 5M | - | - | - | - | - | - | 2000 | 0 | done
77 | 2026-09-30 | 2026-09-30 | NIRMAL SALES AND SERVICES | NS | NUT SET | Nut spare | - | HEX TYPE KEY NUT SET | 1000 | 5M | - | - | - | - | - | - | 1000 | 0 | done
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Consilidated Report
Non-Braided | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15 | Column 16
Sl no. | Customer name | Brand | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total | Type
1 | Aura | WF ST | 0 | 4000 | 5500 | 4000 | 5500 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | PIECES
| Aura | MARINO ST | 0 | 4000 | 4500 | 6000 | 8500 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | PIECES
| Aura | PLAIN ST | 0 | 4000 | 0 | 2000 | 1000 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | PIECES
| Aura | WF CP | 0 | 8992 | 8500 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31492 | PIECES
| Aura | MARINO CP | 0 | 7240 | 14000 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33740 | PIECES
2 | FUTURA | FUTURA ST | 0 | 0 | 25000 | 450 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 33450 | PIECES
3 | BADSHAH BELGAUM | ENFLOW CP | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | PIECES
4 | SURYA TRADING | PLAIN ST | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | PIECES
| SURYA TRADING | SURYA ULTRA ST | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | PIECES
5 | VOJAL | ARTIMIST | 0 | 0 | 0 | 1500 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1950 | PIECES
| VOJAL | VOJAL | 0 | 0 | 0 | 2700 | 1850 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 6650 | PIECES
6 | Pawan Traders | ENFLOW CP | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | PIECES
7 | SK Traders | ENFLOW CP | 0 | 0 | 3000 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7100 | PIECES
8 | Hari Enterprise | ENFLOW CP | 0 | 0 | 1300 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | PIECES
9 | CERAFLO | CERAFLO CP | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | PIECES
10 | NEW POONAM HARDWARE | ENFLOW CP | 0 | 0 | 0 | 1700 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | PIECES
11 | CS WATER TAP | CS WATER TAP ST | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | PIECES
12 | SCHINTLER | SCHINTLER CP | 0 | 0 | 0 | 12500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | PIECES
13 | MAHALAKSHMI ENTERPRISES | ENFLOW CP | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | PIECES
14 | Mathaji electrical hardware and co | ENFLOW CP | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | PIECES
15 | EZIYFLO POLYPLAST | OTTERTEC | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | ROLLS
16 | ASHVA POLYPLAST | AKANT | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | PIECES
17 | Shri Ambika Plast | ENFLOW CP | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | PIECES
18 | TAIBA TRADERS | ENFLOW CP | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | PIECES
19 | BHOOMI ENTERPRISES | ENFLOW CP | 0 | 0 | 0 | 0 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | PIECES
Braided | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15
Sl no. | Customer name | Brand | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total
1 | IDOL | IDOL CP | 0 | 0 | 20200 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30200
2 | AURA | WF CP | 0 | 0 | 0 | 0 | 16000 | 19400 | 0 | 0 | 0 | 0 | 0 | 0 | 35400
| AURA | MARINO CP | 0 | 0 | 0 | 0 | 13500 | 15500 | 0 | 0 | 0 | 0 | 0 | 0 | 29000
3
Nut set | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15
Sl no. | Customer name | Brand | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total
1 | ALPHA SANITARY | NUT SET | 0 | 0 | 3000 | 0 | 4000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
2 | SURYA TRADING | NUT SET | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
3 | GUPTA CROP | NUT SET | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
4 | POWER SKILLS | NUT SET | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
5 | Shri krishna Enterprises | NUT SET | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
6 | Sri Ashapura Industries | NUT SET | 0 | 0 | 30000 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 180000
7 | LOKENATH MEDICAL HALL | NUT SET | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
8 | CR POLYMERSS | NUT SET | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
9 | SHANTI MARKETING | NUT SET | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
10 | PREMIER MARKETING | NUT SET | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
11 | NAVEEN PRODUCTS | NUT SET | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
12 | JJ Marketing | NUT SET | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
13 | BLUE STAR | NUT SET | 0 | 0 | 0 | 0 | 26000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 28000
14 | GATIMAAN ENTERPRISES | NUT SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | BHARUCHI INDUSTRIES | NUT SET | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
16 | LAXMI METAPLAST INDUSTRIES | NUT SET | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
17 | PIPEART | NUT SET | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
18 | RIYYO INDUSTRIES | NUT SET | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
19 | NIRMAL SALES AND SERVICES | NUT SET | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Nut Loose Spare | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12 | Column 13 | Column 14 | Column 15
Sl no. | Customer name | Brand | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total
1 | GUPTA CROP | Nut Loose Spare | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
2 | KANGANA AGENCY | Nut Loose Spare | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
3 | LOKENATH MEDICAL HALL | Nut Loose Spare | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
4 | NAVEEN PRODUCTS | Nut Loose Spare | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000
5 | EZIYFLO POLYPLAST | Nut Loose Spare | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000

## Chart of accounts
Company Name | Brand | Type | Pipe Vendor
AURA | WF ST | Non-Braided | TT
FUTURA | MARINO ST | Braided | GP
ALPHA SANITARY | PLAIN ST | Nut spare | 5M
BADSHAH BELGAUM | WF CP | Nut Loose Spare | ENFLOW2
SURYA TRADING | MARINO CP
GUPTA CROP | FUTURA ST
IDOL | NUT SET
POWER SKILLS | ENFLOW CP
VOJAL | SURYA ULTRA ST
Shri krishna Enterprises | Nut Loose Spare
Pawan Traders | IDOL CP
SK Traders | ARTIMIST
Hari Enterprise | VOJAL
KANGANA AGENCY | CERAFLO CP
Sri Ashapura Industries | CS WATER TAP ST
LOKENATH MEDICAL HALL | SCHINTLER CP
CR POLYMERSS | OTTERTEC
CERAFLO | AKANT
NEW POONAM HARDWARE
CS WATER TAP
SHANTI MARKETING
PREMIER MARKETING
NAVEEN PRODUCTS
JJ Marketing
SCHINTLER
EZIYFLO POLYPLAST
MAHALAKSHMI ENTERPRISES
BLUE STAR
Mathaji electrical hardware and co
EZIYFLO POLYPLAST
GATIMAAN ENTERPRISES
BHARUCHI INDUSTRIES
ASHVA POLYPLAST
LAXMI METAPLAST INDUSTRIES
Shri Ambika Plast
PIPEART
TAIBA TRADERS
RIYYO INDUSTRIES
BHOOMI ENTERPRISES
NIRMAL SALES AND SERVICES